## Slide 1: Professional Services Transition Meeting
PIXARTPRINTING
19/09/2025

## Slide 2: Meeting Agenda
Project Summary
Technical Summary
Recommended Next Steps
2

## Slide 3: Project Summary

## Slide 4
Final Project Status Report – Pixartprinting
Project Summary
More than half of the users have been deployed and there were not any critical issues. Not expected issues during enrollment of remaining users
Today’s Date | Project Dates |  |  | 
19/09/2025 | Start Date | 01/06/2025 | End Date | 19/09/2025
Milestones |  |  | 
Milestone | Baseline Date | Target Completion Date | Status
Initial Project Schedule Accepted | 27/06/2025 | 27/06/2025 | 
Initial Design Accepted | 14/07/2025 | 17/07/2025 | 
Pilot Configuration Complete | 28/07/2025 | 18/07/2025 | 
Pilot Rollout Complete | 08/08/2025 | 22/08/2025 | 
Production Configuration Complete | 29/08/2025 | 29/08/2025 | 
Production Rollout Complete | 19/09/2025 | ?? | 
Final Design Accepted | 19/09/2025 | 19/09/2025 | 
User Rollout Roadmap |  |  |  | 
Milestone | Target Users | Current Users | Target Completion | Status
Pilot | 100 | 449 | 19/09/2025 | 
Production | 800 | 449 | 19/09/2025 | 
Project Status
Scope | Schedule
Planned Project Objective (Target) | Actual Project Result (Actual) | Deviation/ Cause
Protect and Secure Internet Access for Users | More than half of the users have Zscaler Client Connector deployed and are fully protected when they are outside of the corporate office | Not enough time to deploy ZCC in all users but deployment is on track to be finished by Pixartprinting and no critical issues are expected.
Complete user posture | Users and devices are identified, and policies can be applied based on this criteria | No deviations
Comprehensive Web filtering | Web filtering based on reputation and dynamic categorization rather than simply categories. | No deviations
Notes: Who: External & Internal Project Team
What: Project Status Report
When: Weekly
Why: Keeps project stakeholders informed on a weekly basis on critical aspects of the project such as scope, schedule, risks, issues, and next steps.
Mandatory: Yes (all projects)
RAG Status Key:
Red - Not On Track
Amber - At Risk
Green - On Track
Blue - Complete
Gray - Not Started

## Slide 5: Deliverables
Deliverable | Date delivered
Kick-Off Meeting and Slides | 27/06/2025
Design and Configuration of Zscaler Platform (per scope) | 30/06/2025 – 11/07/2025
Troubleshooting Guide(s) | 18/07/2025
Initial & Final Design Document | 17/07/2025 – 17/09/2025
Transition Meeting Slides | 19/09/2025

## Slide 6: Technical Summary

## Slide 7: Deployed ZIA Architecture
User authentication and provisioning
Central Authority
1
3
Z-Tunnels
Policy
4
2
Public Service Edges
SaaS | Internet
SSL Inspection
Workforce (Region-X)
On | Off - net
Z-Tunnels
SSL Inspection
Workforce (Region-Y)
On | Off - net
Admin Console
Logging
5
Authentication Type | 
Identity Provider | Entra ID
Authentication Type | SAML 2.0
User and Group Provisioning | SCIM Provisioning
Client Deployment | 
Tunnel Type | ZCC with Z-Tunnel 2.0
ZCC Deployment System | MS Intune/Jamf
Number of Windows and MacOS Devices | 351 Windows Devices 98 MacOS Devices
Geo Locations | Europe, North Africa, USA
Policy Deployment | 
SSL Inspection Policies | 10 Policies
URL Filtering Policies | 5 Policies
Cloud App Control Policies | 5 Policies
Firewall Policies | 15 Policies
Identity
Notes: An overview of the deployed architecture and key facts - diagram stays generic (custom diagram will be in design document)
Numbers on the diagram help to orient the conversation,

## Slide 8: Open Items
Task/ Description | Date | Owner | Transition Plan/ Next Steps
Finish Production rollout | October 2025 | Pixartprinting | Onboard remaining users from all departments including Developers.
Tighten Firewall policies | October 2025 | Pixartprinting | Change the default Firewall rule from Allow All to Block All after configuring all the required exceptions.
Tighten Cloud App Control Policies | October 2025 | Pixartprinting | Configure block policies for high risk applications in all categories.
Fine tune SSL Inspection policies | November 2025 | Pixartprinting | Continue adjusting and adding exclusions to SSL Inspection policies as required.
Configure DLP policies | December 2025 | Pixartprinting | Configure DLP policies to control sensitive data and avoid potential data leaks.
Deploy ZCC on Mobile devices | January 2026 | Pixartprinting | Expand the deployment of Zscaler Client Connector to Mobile devices.

## Slide 9: Recommended Next Steps
Short Term Activities
Finish Production rollout.
Tighten Firewall policies.
Tighten Cloud App Control Policies.
Fine tune SSL Inspection policies.
Configure Role Based Access Control (RBAC).
Configure DLP policies.
Long Term Activities
Deploy ZCC on Mobile devices.
Consider an upgrade of Sandbox license to have better antimalware protection.
Consider an upgrade of the Firewall License to be able to apply policies based on user groups and network applications.
Adopt additional Zscaler solutions like Zscaler Private Access (ZPA) or Zscaler Digital experience (ZDX).
Consider using ZCC Client when the users are on-prem for a more consistent user experience.
Integrate ZIA with 3rd party SIEM.
Notes: Next Short- and Long-Term Activities
If additional resources and/or expertise are required to complete any of the recommendations above,customer should consider engaging Zscaler Professional Services to assist with this effort.

## Slide 10: Thank you
Your feedback on our project and Professional Services team is important to us.
Project Manager: Alex Vazquez
Consultant: Alex Vazquez
A short ~6 question survey on how your Professional Services team did will be automatically sent after the project has closed. The following people will receive the survey via email:
Primary Contact: Teia proctor
Secondary Contact: Marco Sattier
We appreciate any insights you can provide to help us improve our processes and ensure we provide the best possible service in future projects.
We want to know!

## Slide 11: Thank you